## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. |  | Passed
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. |  | Passed
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. |  | DV; 04/02; Unable to see message after fulfilling needs as a user. When all quanities are donated, maybe display no needs. | Pass | NC, fixed issue, when quantity hits zero the need is now removed
| Given that I am on the Needs page when there are needs in the cupboard I can choose a need to see the details and short description |  | DV; 04/02; Just cost and name | Pass | NC, 4-02-24. False fail, wording on test was bad
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. |  | Passed
User Login / Store basket (8 points) |  |  | Passed
As a visitor I want to user authentication so that I can store user data to a cart. | **Given** I log in with a username **when** no username exists **then** then I will be a new user. |  | DV ; 04/02; 1) When no username exists in the login, it logs me in. However, if you log out and type in the box, it doesn't allow for us to log back in if no username exist the second time. On the backend, if the user is not provided, it is listed as null. But, when typed in as null, the user is "null" in the backend. 2) When a long username is typed, I get a 400 request and no user created. | Pass | NC - 4/2/24. Fixed bug, must enter usernsame to continue
| **Given** I log in with a username **when** the username exists **then** my basket should load when I go to basket |  | TL; 04/02; If a null username is created, meaning logging in with nothing in the username, you can not create any new users. | Pass | NC- 4/2/24. Fixed bug, cannot login with null username
| **Given** I log in with a username **when** the username is "admin"**then** the system should treat me as admin see: |  | Passed
User Checkout (8 points)
As a helper I want to checkout so that I purchase items in my cart | **Given** I submit a request to checkout **when** my basket has needs stored within it**then** the checkout will show and remove needs in the basket (making them no longer available for purchase) |  | Passed
| **Given** I submit a request to checkout **when** my basket has NO needs stored within it**then** nothing should show |  | Passed
Admin Login (5 points)
As a U-Fund Manager I want to login in with admin access so that I can edit needs. | **Given** I provide a username **when** that username is "admin" **then** it should log me in as a admin allowing me extra permissions |  | Passed
| **Given** I provide a username **when** that username is not "admin" **then** the system should not log me in as a admin and instead treat me as a user. |  | Passed
Add need to basket (3)
As a helper I want to add needs to my basket so that I can purchase them. | **Given** I submit a request to add a need to my basket **when** need is still available **then** said need will be in the user's cart |  | Passed
| **Given** I submit a request to add a need to my basket **when** need is not still available in persistent storage **then** nothing will happen |  | Passed
Get Entire basket (3 points)
As a User I want to retrieve my whole basket so that I can see what items I have added to it . | **Given** I submit a request for the basket **when** needs are in the basket **then** a list of needs will show |  | Passed
| **Given** I submit a request for the basket **when** no needs are in the basket **then** a empty list of needs will show |  | Passed
Remove need from basket (3)
As a helper I want to remove needs from my basket so that I have flexibility in which items I purchase. | **Given** I submit a DELETE request for a need **when** this need is within the persistent storage for my basket **then** the need will be removed from the basket |  | Passed
| **Given** I submit a DELETE request for a need **when** this need is not within the persistent storage for my basket **then** nothing happens |  | Passed
Implement UI (21)
As a helper I want to have a user-friendly screen design so that I can easily donate needs and/or become a partner. | **Given** Maven is running **when** Start angular server **then** Have the system display the list of needs |  | Passed
| **Given** There are needs in the list **when** button to delete **then** delete the need |  | Passed
| **Given** There are fields filled out **when** button to add **then** add a need |  | Passed
| **Given** There are needs in the list **when** button to add to basket **then** add to basket and display |  | Passed
Get Entire Basket(3 points)
As a user I want to retrieve a whole basket so that I can see what items are within it . | **Given** I submit a request for the basket**when** needs are in the basket**then** then the basket will show. |  | Passed
| **Given** I submit a request for the basket**when** no needs are in the basket**then** then nothing will show in the basket |  | Passed
| Given I submit a request for a basket when the basket does not exist then the system should return an empty list with status code of 404 (NOT FOUND) |  | Passed
Add need to Basket(3)
As a User I want to submit a request to add needs to a basket so that I can populate baskets. | **Given** I submit a request to add a need to my basket**when** need is still available **then** said need is added to user's basket |  | Passed
| **Given** I submit a request to add a need to my basket**when** need is not still available in persistent storage **then** nothing will happen |  | Passed
| **Given** I submit a request to add a need to my basket**when** need is already within in the basket**then** the quantity of the toy item will update |  | Passed
Story: Search Needs/ Main Page Dashboard (5)
As a helper I want to have a user-friendly screen design so that I can easily donate needs and/or become a partner. | **Given** There are needs **when** typing in the need search **then** Needs sharing similar parts to the search will appear |  | Passed
| **Given** There are needs **when** visiting the main dashboard **then** Display all needs and search bar |  | Passed
Story: User Basket Checkout (8 points)
As a helper I want to checkout so that I purchase items in my basket. | **Given** I submit a request to checkout **when** my basket has needs stored within it **then** the needs will be removed (making them no longer available for purchase) |  | Passed
| **Given** I submit a request to checkout **when** my basket has NO needs stored within it **then** the system should checkout an empty list, therefore doing nothing |  | Passed
Story: Basket Dashboard (5 points)
As a helper I want to have a user-friendly screen design so that I can easily view my basket, remove items from it and checkout. | **Given** I want to view my basket**when** click a view basket button **then** I expect to see the toys within my basket. |  | Passed
| **Given** I want to remove an item from my basket **when** I click a button **then** I expect to see have the toy removed from my basket |  | Passed
Login Page/Logic (13 points)
As a helper I want to have a user-friendly screen design so that I can easily donate needs and/or become a partner. | **Given** I want to log in to smiles unlimited **when** I type my username in **then** I want to be able to see whatever information and options I have access to. |  | DV; 04/02; When logged in and change id, I am no user and not able to view anything like cart, need, etc. | Pass | NC - 4/02/24. Security concern that is not needed for this project. Everything works as expected
User Login / Logout & Store Basket(8 points)
as an admin I want to user authentication so that I can store user data to a basket. | **Given** I log in with a username **when** no username exists **then** the system should add username to persistent storage to save data and (tie a shopping basket to it) |  | Passed
| **Given** I log in with a username **when** the username exists **then** then the basked will be saved for later |  | Passed
| **Given** I log in with a username **when** the username is "admin"**then** the system should treat me as admin |  | Passed
Admin Login (5 points)
As a U-Fund Manager I want to login in with admin access so that I can edit needs. | **Given** I provide a username **when** that username is "admin" **then** the system should log me in as a admin allowing me extra permissions. |  | Passed
| **Given** I provide a username **when** that username is not "admin" **then** the system should not log me in as a admin and instead treat me as a user. |  | Passed
Special Feature: Application for Partnership (13) |  |  |  | Pass | NC - 4/2/24
As a Partner I want to request partnership so that I can request toys and money through the U-Fund Manager. | **Given** application includes all required criteria **when** User submits application **then** the application will be saved and return status code 201 (CREATED). |  |  | Pass | NC - 4/2/24
| **Given** application does not include all required criteria **when** User submits application **then** the application will not be saved. |  |  | Pass | KK - 4/2/24
Special Feature: Email Receipt (8) |  |  |  | Pass | KK - 4/2/24
As a buyer I want to receive a receipt of my purchase so that I can review my purchase. | **Given** I request to a receipt after checkout with given email **when** this email is valid **then** the system should send receipt |  |  | Pass | KK - 4/2/24
| **Given** I request to a receipt after checkout with given email **when** this email is not valid **then** there wont be an email |  |  | Pass | NC - 4/3/24
Story: Admin UI Page Add New Need(5 points) |  |  |  | Pass | NC - 4/3/24
As a helper I want to have a user-friendly screen design so that I can easily donate needs and/or become a partner. | **Given** logged in as admin **when** I fill out the given fields and press add a toy button **then** I expect a toy to be added |  |  | Pass | NC - 4/3/24
**Given** logged in as admin **when** I edit a toy **then** I expect a blank toy to be changed
Extra Bug | Admincannot add update/add negative values for cost and quantity |  | Unable to find: DV ; 04/02; When editing a need's cost, I can set a negative value like -200 | Pass | NC - 4/3/24, admin can not add neagtive values when update or add